*DRILLING REPORT REFLECTS OPERATIONS AS OF 7:00 AM*

3/6/20	Moving in rig.

3/7/20	40’ (40’) Drilling. Spudded at 11:00 pm on 3/6/20.

3/8/20	505’ (465’) Drilling. Deviation 0.5° at 278’.

3/9/20	1340’ (835’) Drilling.

3/10/20	1770’ (430’) Finishing cementing surface casing. Set 8 5/8” casing at 1763’ with 650 sx 65/35 POZ tailed by 150 sx Class C cement. Circulated 30 bbl cement to surface. Deviation 0.75° at 1770’.

3/11/20	1935’ (165’) Drilling.

3/12/20	2290’ (355’) Reaming/drilling.

3/13/20	2400’ (110’) Drilling.

3/14/20	2453’ (53’) Drilling.  Deviation 3/4°

3/15/20	2610’ (157’) Drilling.

3/16/20	2991’ (381’) Drilling.

3/17/20	3446’ (455’) Drilling.

3/18/20	3939’ (493’) Drilling.

3/19/20	4335’ (396’) Drilling. Deviation 0.75° at 3945’.

3/20/20	4615’ (280’) Circulating hole clean at core point.  Will do short trip and come out of hole and prep to start coring.

3/21/20	4615’ (0’) Reaming with core barrel.

3/22/20	4622’ (7’) Coring.  Started coring at 4615’.

3/23/20	4683’ (61’) Coring. Recovered complete core #1 from 4615’ – 4676’.

3/24/20	4769’ (86’) Coring. Recovered complete core #2 from 4676’ – 4736’.

3/25/20	4880’ (111’) Preparing to start coring. Recovered complete core #3 from 4736’ – 4796’. Deviation 0.25° at 4880’.

3/26/20	4934’ (54’) Coring. Recovered partial core #4 from 4880’ – 4897’.

3/27/20	5109’ (175’) Drilling. Recovered complete core #5 from 4897’ – 4957’.

3/28/20	5380’ (271’) Waiting on new bit, preparing to ream.

3/29/20	5380’ (0’) Preparing to core.

3/30/20	5439’ (59’) Tripping in hole for DST #1. Recovered complete core #6 from 5380’ – 5439’.

3/31/20	5439’ (0’) Tripping in hole to resume drilling. Tried to run DST #1 but hit a bridge at 2046’.

DST #2 Lower Mississippian 5379’ – 5439’

Rec: 40’ mud

36-41/1376#, 41-50/1374#

4/1/20	5640’ (201’) Tripping in hole to core #7. Deviation 1° at 5640’.

4/2/20	5719’ (79’) Tripping out of hole with core #8. Recovered partial core #7 from 5640’ – 5670’. Recovered partial core #8 from 5670’ – 5719’.

4/3/20	5780’ (61’) Tripping out of hole, preparing to core.

DST #3 Viola 5640’ – 5710’

Rec: 300’ mud cut water (5% mud, 95% water)

52-115/1477#, 104-164/1474#

4/4/20	5814’ (34’) Coring. Recovered partial core #9 from 5780’ – 5811’.

4/5/20	5826’ (12’) Letting LCM pill set. Recovered partial core #10 from 5811’ – 5826’. Lost circulation at 5826’. Recovered full returns, went in with conventional bit and then lost returns. Mixed LCM pill to displace out of pipe and let set.

4/6/20	5850’ (24’) Tripping out of hole with core tool. Resumed drilling conventional from 5826’ to 5850’. Attempted to core at 5850’ but lost circulation again. Did not continue coring.

4/7/20	5865’ (15’) Drilling with conventional bit.  Regained circulation and resumed drilling with conventional bit.

4/8/20	5959’ (94’) Reaming to prepare for next core #11.

4/9/20	6019’ (60’) Tripping in hole for next core #12. Recovered complete core #11 from 5,959’ – 6,019’.

| Core | Interval | Feet Cored |
| --- | --- | --- |
| Core #1 | 4615’ – 4676’ | 61’ |
| Core #2 | 4676’ – 4736’ | 60’ |
| Core #3 | 4736’ – 4796’ | 60’ |
| Core #4 | 4880’ – 4897’ | 17’ |
| Core #5 | 4897’ – 4957’ | 60’ |
| Core #6 | 5380’ – 5439’ | 59’ |
| Core #7 | 5640’ – 5670’ | 30’ |
| Core #8 | 5670’ – 5719’ | 49’ |
| Core #9 | 5780’ – 5811’ | 31’ |
| Core #10 | 5811’ – 5826’ | 15’ |
| Core #11 | 5959’ – 6019’ | 60’ |
| Total Feet Cored To Date: |  | 502’ |